## JCI-YORK 6-9-10
SANDRIDGE CENTURY PROJECT TRAIN 1
| JOHNSON CONTROLS INC- YORK COMPRESSORS DAILEY REPORT |  |  |  |  | DATE: 6/ 26 /10
REPORT BY: |  | Jerry Kirwan |  |  |  | REV. 0 | BJ
NAMES |  |  | WORK TYPE: (CHECK ONE) |  | INSTALLATION | WARRANTY
CREW CHIEF: | JERRY KIRWAN |  |  | C-1231A | X
PROGRAMMER: | JOE TORO |  |  | C-1231B | X
MECHANIC: |  |  |  | C-1231C | X
MECHANIC: |  |  |  | C-1231D | X
MECHANIC: |  |  |  | C-1231E | X
MECHANIC: |  |  |  | C-1231F | X
Equipment # | Checklists/ Field Findings |  |  |  |  | Status
C-1231A | Axial Spacing check |  |  |  |  | PENDING
| Transmitter(s) - Re-install |  |  |  |  | PENDING
| Preperation of package for DCS Loop testing |  |  |  |  | Complete
| Copressor Sump Oil Change out as previously agreed upon |  |  |  |  | PENDING
| XV-1231A4 LCD issue may be corrected (Reavaluate fix on 6/26) |  |  |  |  | PENDING
| PV-1231A1 4 to 20 ma signal on TX was reversed to match drawings |  |  |  |  | Complete
| JCI, OXY, & Mustang ringout out of all signals to the DCS |  |  |  |  | Started
FV-1231A1 wouldn't acctuate - James the Instument lead took an air regulator off to
| evalute for repair |  |  |  |  | PENDING
C-1231B | N2 purge @ 0 psi - Unit open for work - |  |  |  |  | NOT OK
| Copressor Sump Oil Change out as previously agreed upon |  |  |  |  | PENDING
| Preperation of package for DCS Loop testing |  |  |  |  | STARTED
C-1231C | N2 purge @ 0 psi - Unit open for work - |  |  |  |  | NOT OK
| 480 VT power - Transformer connection correction |  |  |  |  | PENDING
| Copressor Sump Oil Change out as previously agreed upon |  |  |  |  | PENDING
C-1231D | N2 purge @ 8 psi (needs reavaluated) |  |  |  |  | PENDING
| Copressor Sump Oil Change out as previously agreed upon |  |  |  |  | PENDING
| 480 VT power - Transformer connection correction |  |  |  |  | PENDING
| Transmitter(s) - Re-install |  |  |  |  | PENDING
C-1231E | N2 purge @ 0 psi - Unit open for work - |  |  |  |  | PENDING
| Interconnecting Piping - re-install |  |  |  |  | COMPLETE
| Fiber-optic connections (Test HMI that was not communicating) |  |  |  |  | COMPLETE
| 480 VT power - Transformer connection correction |  |  |  |  | PENDING
| Transmitter(s) - Re-install |  |  |  |  | PENDING
| Copressor Sump Oil Change out as previously agreed upon |  |  |  |  | PENDING
C-1231F | N2 purge @ 10 psi |  |  |  |  | OK
| Interconnecting Piping - re-install |  |  |  |  | STARTED
| Copressor Sump Oil Change out as previously agreed upon |  |  |  |  | PENDING
| 480 VT power - Transformer connection correction |  |  |  |  | PENDING
| Transmitter(s) - Re-install |  |  |  |  | PENDING
| Discovered HMI display was overheating & shutting down |  |  |  |  | Complete
COMMENTS/OTHER:
| All previous alignment records will be reviewed against parameters. |  |  |  |  | PENDING
| XV-1231A-4: Defective position transmitter - Looks good now that water has been |  |  |  |  | Reviewing
removed from housing (will continue to monitor)
Attended meeting with Sandridge & other vendors discussing startup schedule.
JCI requests information on what is going to be done about the missing hot gas bypass
checkvalves CV-1231AO & CV1231A7 (typical of the other two suction lines)
| Will work on replacement of HMI display on 1231F on Monday |  |  |  |  | PENDING